NSW is a lucky State
I was going to write about NSW wind farm progress. But there is nothing to write about.
There is probably a lot of talk going on at the clean energy summit. Talk is about all the industry does these days and the Summit is no doubt a good place to do it.
For the record Uungula was the last wind farm to reach FID in NSW in Dec ‘23’ more than 30 months ago.
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NSW Wind Farms — Construction Progress

Key findings as at late July 2026 — no FIDs, financial closes or new PPAs since April
. Under construction Approved — awaiting finance . Outstanding issue Abandoned

Project MW Status NSW EPBC Comment Source

Uungula 414 Under construction v/ v/ Towers rising since early June; blade Squadron Energy,
deliveries cleared 20 Jul. Energisation Jun-Jul 2026
late 2026 / early 2027.

Pottinger 831 FID pending v/ v/ Fully approved. "Late 2026" construction Someva, 18 Jun 2026;
restated Jun 2026. AGL FY26 results RenewEconomy
(Aug) the next signal.

Liverpool Range 634 FID "end 2026" v/ v/ Tilt's $2.25bn July refi funds Waddi + Tilt Renewables,
Palmer — NOT Liverpool Range. Only "site 17 Jul 2026
investigations" June update.

Yanco Delta 1,460 Equity raise live 7t 7t Origin restarted ~80% sell-down 24 Apr ION Analytics,
(Barrenjoey; ~$5bn project). Debt raise 24 Apr 2026
end-2026, FID mid-2027.

Hills of Gold 372 Quiet since court win v v No next-steps announcement in the four Someva news feed,
months since the Mar 2026 settlement. Apr-Jul 2026

Coppabella 289 BESS approved, no FID v/ v/ Decentralised BESS mod (~1,060 MWh) NSW planning portal,
approved 3 Jul. Wind farm shovel-ready, 3 Jul 2026
still waiting on Goldwind.

Valley of the Winds 943 Judgment reserved Ve v Baillieu Class 1 merits appeal heard IPC NSW; Coonamble
1 Jul 2026, Dubbo LEC. No PPA; parent Times, Jul 2026
ACEN capital-constrained. FID 2027+.

Spicers Creek 700 CIS re-tender v/ v/ Invited to re-bid CIS contract — costs The Energy,
up 50-60% since 2023. FID beyond 2026. 18 May 2026

Dinawan ~707 Wind DA pending X X Wind farm still at RTS stage. FC target NSW planning portal,
end-2026 hard to reconcile. Solar+BESS Jul 2026
approved (solar EPBC 7 Jul — wind not
covered).

Bullawah ~804 IPC hearing pending X X Public hearing requested Feb 2026; IPC IPC NSW; BayWa r.e.,
process not commenced. Q3 target gone. Jul 2026
Parent BayWa AG distressed.

Winterbourne ~731 IPC hearing pending X X Hearing ordered Feb 2026 (first for a IPC NSW; Vestas
wind farm); DPHI referral still pending. timeline — 28 Jul 2026
1,371 submissions, 56% in support.

Determination expected early 2027.

Boorolong 426 Abandoned — — Squadron discontinued 17 Jul after RenewEconomy,

pipeline review; Jeremiah also withdrawn. 17 Jul 2026

NSW = state development consent (SSD). EPBC = federal environmental approval. * Valley of the Winds consent is under Class 1 merits appeal — judgment reserved.
T Yanco Delta original approvals (Dec 2023 / Feb 2024) stand, but the revised construction layout is still pending: SSD MOD 2 at response-to-submissions; EPBC re-referral 2025/10179 undecided.

Approval is no longer the binding constraint — finance is

Eight projects hold both state and federal approval; none reached FID this quarter. NSW carved out of federal CIS Tender 9; state LTESA
Tender 8 (2.5 GW) opened May with "sculpted pricing". Squadron: costs up 50-60% since 2023; Spicers Creek invited to re-tender its CIS contract.

Data: Squadron Energy, Origin Energy, AGL/Someva, Tilt Renewables, Spark Renewables, IPC NSW,
NSW planning portal, RenewEconomy, ION Analytics, The Energy, ITK Services — compiled 28 Jul '26




